## Original Scope - Retail
Modules | Features | Interactions | Notes | Questions/Clarifications | Answers
Login | Email ID | - | -
| Password | - | - | - | Only corporate Email IDS - No Google or other personal EMail IDs
| Google Sign in | - | - | Do we need to implement 2Fac Auth? The simplest way is email OTP signin | NO 2 Factor needed
Forget Password | Password reset | Email reset link trigger | - | - | NO
| Password confirmation | Page to recreate the password | After the password reset, the user will be redirected to the Login page | -
Signup | First Name | - | - | Do we need to send email confirmation on the password reset?
| Last Name | - | - | -
| Email ID | - | - | -
| Password | - | - | Do we need to restrict to only work Email ID? Do we need to restrict the domain to the business name? | Yes, only work IDs required
Onboarding | Step form - 1 (User Details) | First Name Last Name Email Address | Autopopulate the details from Signup Business name will be populated from email domain | - | NO
| Step form - 2 (Business Details) | Business Name Add Company Logo Add Company Headshot Primary Color selection Custom Disclosures | Business name will be populated from email domain | The step 1 can be mereged with the Signup
| Step form - 3 (Preview) | User preview | All the details will be previewd Edit functionality will take the user to the step | By default we are taking one user at a time. What time of role based access do you want? - One user | Don't fulyl understand the question, can discuss in kickoff meeting
Subscription | Plans Selection | Feature listing | List down all the features offered | Should first-time users be guided with onboarding tooltips or tutorials? Is there a welcome deck or sample demo for new users? | NO
| Confirmation | Payment details | Stripe integration Payment confirmation | Any features that are available on both tiers? Any restrictions on the trial? Based on the plan - what would be the number of user | Only 1 pricing option, 7 day free trial. The trial will have no resteictions but will need a credit card for signing up which we will charge after 7 days.
Dashboard | Navigation bar | Scatterplot x Company logo Menu items | Company details | Please confirm if you want to give a month trial and then the subscription will start | 7 Day trial
| User Metrics | Graphs (if required) | - | Only one company is confirged post signup
| Featured section | Featured formats of PPT | Categories, Topics, Sub-categories | If we need to add few key metrics like no of decks created, no of emails shared, etc. | NO
| PPT view | List of PPTs created | List and grid view | -
Slides Library | Search Slides | Ability to search and filter templates by name, category, topics | -
| Filtering the Slides |  | - | -
| Slides view | List of all the slides | Ability to view the content of the slides Ability to download Ability to copy key points See the latest updated date recurring count of the data updationm - 'Updates Daily' | -
Deck Creation | Creation flow | List of PPTs selected | Ability to view the slides selected - multiple categories can be selected | As we understood, the talking points is nothing but a description of the chart. Please let us know if there any further functionalites to make it more dynamic | Nothing dynamic, just talking point. These talking points will get renewed perodically.
|  | Ability to rearrange | Ability to rearrange the slides or delete from the deck
| Preview flow | Preview the Deck | Final preview with the cover slide and conclusion | -
|  | Preview the talking points | Preview of a summary of all the talking points - AI generated | Do we need to give an ability where the user have options to select layout from a predefined set of slides? | No, during signup when they add thier logo, colours and disclosure all the slides they view will auto update and no other customization needed.
|  | Set an email body and mailing list | Ability to send emails to individuals and groups/organisation On confirming, the email will be sent with key talking points and PDF of the PPT | Need to specify the character limit - N/A | I dont understand, we can chat during the meeting
|  | Ability to download | User can download the whole deck | We may need to do a feasibility on the approach where if the system sends out the email then the signature may not be added | the system will not send out any emails. The cleint can copy paste and send the emails to thier cleints.
Deck Management | Key Metrics | Grid view of key metrics | No of recurring slides, No of total decks, No of Org | -
| History | Total list of all the decks | Ability to search, filter and sort | -
|  | Deck overview | Details like: 1. Email recipients 2. Email body 3. Slides sected 4. Date and timestamp of email sent | -
User Management | List of all the contacts | - | - | -
| Abiltiy to add/delete/edit contacts | - | - | -
| Group/Org management | Ability to create groups Ability to add/remove users to a specific group | - | -
Profile section | Business overview | Details of the company - ability to update the details like Logo, color, address, other details | - | -
| Personal information | User information | The user will not be able to change the email ID | -
| Subscription details | Plan details Feature list Ability to download the invoice Upgrade/Downgrade the plan | - | -
| Logout | - | - | If the user downgrades, what features should we restrict? Do we need add auto renewal? | They lose all access
Notifications | Trigger notifications on a specific event | System and email notification will be sent to the user | Please let us know which specific events needs to be notified. Ideally, it should be for reminders on any slide change, new trending topics, general push notifications | -
| Detail redirection | Clicking on the notification will redirect to the respective page | - | -

## Scope - Admin
Pages | Features | Interactions | Notes | Questions/Clarifications | Answers | Design Rough Estimates | FE Rough Estimates | BE Rough Estimates
Login and reset password | Email ID |  |  |  |  | 6 | 4 | 2
Password
Dashboard | Metrics | 1. User Metrics (No of user signedup - that month) 2. No of templates created | Slide performance metrics (conversion impact) Track most-used slides/decks |  |  | 24 | 16 | 24
| List view of users / recent subscriptions |  | New users, total users, users frequently using the platform, user retention
List of decks created
Slide management | Creation and edit flow (adding key points) | Abitlty to create new slides and categories Either with set layout templates where you can only change the chart type and content or with advanced customisation like google slides | Chart library, text formatting, color formatting?, adding shapes. OR Have a set template for layout and the admin will only be able to change the chart option, topic and description content. (Decision to categorise whether the slide will update daily, monthly or will be static) | How advance do we want to add the creation features Should the manual creation of the slides for the MVP follow the same steps, that we are planning to add from the admin panel? If we need to send the update on the new slide creation - should it be shown in as an in-app notif or do you want to trigger a system email? |  | 20 (UX research & Strategy, UI research, design & prototype) | 24 | 32
| Preview flow | Final preview of the slides created |  |  |  | 32
| Key Metrics |  | Metrics accoring to the creation (total slides, slide updates) |  |  |  | 8 | 10
Search & Filters Slides
Slides list
| Version History of slide edits |  | matching the design and layout with the other products with the same feature for best user experience
User Management | List of all the contacts with Group/Org management | Ability to visualize the user details with org/group filter | - | - |  | 14 | 4 | 8
| List of active/inactive subscriptions | with account summary of the users | - | - |  | 8 | 8 | 24
Subscription Management | Create/change subscription plan | - | - | After changing in price of plan, do we need to add user consent with the new price ?
| Stripe data CORS | Total invoice value Payout details | We need to check if we can show the total ticket size of that month and also highlight the payout bank details | Do we need to provide invoice to the user? Do we need to create invoice from the Scatterplot?
Profile | User details |  |  |  |  | 10 | 2 | -
| Notification | Contact us? new subscribers?
Logout
[6 empty] | 94 | 66 | 100
190
166
190.9

## Scope - Landing page
Pages | Features | Interactions | Notes | Questions/Clarifications | Answers | Design Rough Estimates | FE Rough Estimates | BE Rough Estimates
Home page | Hero Section | Product Preview |  |  |  | 20 | 10-12 hours (Code refactoring) | 8 H (If any dynamic content is required from BE then and only then)
Intro
CTA
| Trust Banner | Expertise, supporters |  |  |  | 4
Reviews, adopters, number of users
| What it does + Value Proposition | Features |  |  |  | 6
Value it creates - How much time it saves, How accuracy helps, etc
| Who all can use it | User personas who can benefit |  |  |  | 3
| How it works | 3 to 4 Steps |  |  |  | 6 (with narrative, layout and no animation) 12 - if with 4 illustrations only 28 - if with 4 animations
3 to 4 illustrations or Animations
| Pricing |  |  | ?? |  | 4
| FAQs | Ask and get answers (AI?) |  |  |  | 3
| CTA Section | Product Preview |  |  |  | 3
CTA
| Footer |  |  |  |  | 6
[5 empty] | Ballpark | 55-80 hours

## Scope - Branding
Pages | Features | Design Rough Estimates
Logo Design | Logo mark, full logo | 24 (with initial brand and field research, understanding the vision mission, client's POV)(iterations)
Colored, black, white
Color Palette | Primary, secondary, Accents | 4
Grayscale
Persona | Brand Personality | 12 (with initial brand and field research, understanding the vision mission, client's POV)
Tone of communication across touch points
Brand guidelines | Usage rules | 8
Application | Favicon | 4
Email signature

## Sheet7
Modules | Estimated Design Efforts in Hours | Signed-up Design hours | Estimated FE Efforts in Hours | Signed-up FE hours | Estimated BE Efforts in Hours | Signed-up BE hours | Estimated QA Efforts in Hours | Signed-up QA hours
Original Scope_Retail | 134 | (40+150)*1 | 256 | (80+160)*1.5 | 406 | (80+160)*1.5 | 60 | 80*1.5
Admin | 94 |  | 66 |  | 100 |  | 40
Landing Page | 80 |  | 12 |  | 8 |  | 16
Branding (Logo) | 16 - 24
| 308 | 190 | 334 | 360 | 514 | 360 | 116 | 120
| 328 | 190 | 334 | 360 | 514 | 360 | 116 | 120
To be signed up |  | 138 |  | -26 |  | 154

## Sheet8
Modules | Service | Start Date | End Date | Timeline
Original Scope_Retail | Design | 2025-07-21 | 2025-08-20 | Design ~ 1 Month | Prathmesh - Sr. Product Designer - 40 hrs/month Krishna - Product Designer - 150 hrs/month
| Dev | 2025-07-29 | 2025-09-05 | Dev ~ 1.5 Months | Surbhi - Sr. Frontend Engineer - 80 hrs/month Jugal - Frontend Engineer - 160 hrs/month Rohan Ghodke - Sr. Backend Engineer - 80 hrs/month Parth Jasani - Backend Engineer - 160 hrs/month Yashaswi - Quality Analyst - 80 hrs/month
Enhancements | Design | 2025-08-21 | Sept 10 | Design ~ 3 Weeks (125 - 130 Hours) | Prathmesh - Sr. Product Designer - 40 hrs/month Krishna - Product Designer - 150 hrs/month
| Dev | 2025-09-06 | 2025-10-05 | Dev ~ 1 Month (230 Hours) | Surbhi - Sr. Frontend Engineer - 80 hrs/month Jugal - Frontend Engineer - 160 hrs/month Rohan Ghodke - Sr. Backend Engineer - 80 hrs/month Parth Jasani - Backend Engineer - 160 hrs/month Yashaswi - Quality Analyst - 80 hrs/month
Retail - Extension - 1 to 1.5 Months |  |  |  |  | Surbhi - Sr. Frontend Engineer - 40 hrs/month Jugal - Frontend Engineer - 160 hrs/month Dakshay - 80 Hours/Month - Non billable for 2 months (Total 160 Hours) Arpit - Backend Engineer - 160 hrs/month Parth Jasani - Backend Engineer - 160 hrs/month Yashaswi - Quality Analyst - 160 hrs/month
Billable Table | Unbillable | Cost Optimization
Surbhi - Sr. Frontend Engineer - 40 hrs/month Jugal - Frontend Engineer - 160 hrs/month Arpit - Backend Engineer - 160 hrs/month Parth Jasani - Backend Engineer - 160 hrs/month Yashaswi - Quality Analyst - 160 hrs/month | Dakshay - S/w Engineer rate - 80 Hours/Month | Surbi - 40 Hours

## Original Scope - Admin (hidden)
Pages | Features | Interactions | Notes | Questions | Answers
Login | Email ID | - | - | - | Only corporate Email IDS - No Google or other personal EMail IDs
| Password | - | - | Do we need to implement 2Fac Auth? The simplest way is email OTP signin | NO 2 Factor needed
| Google Sign in | - | - | - | NO
Forget Password | Password reset | Email reset link trigger | - | -
| Password confirmation | Page to recreate the password | After the password reset, the user will be redirected to the Login page | Do we need to send email confirmation on the password reset?
Signup | First Name | - | - | -
| Last Name | - | - | -
| Email ID | - | - | Do we need to restrict to only work Email ID? Do we need to restrict the domain to the business name? | Yes, only work IDs required
| Password | - | - | -
| Google Sign up | - | - | - | NO
Onboarding | Step form - 1 (User Details) | First Name Last Name Email Address | Autopopulate the details from Signup Business name will be populated from email domain | The step 1 can be mereged with the Signup
| Step form - 2 (Business Details) | Business Name Add Company Logo Add Company Headshot Primary Color selection Custom Disclosures | Business name will be populated from email domain | By default we are taking one user at a time. What time of role based access do you want? | Don't fulyl understand the question, can discuss in kickoff meeting
| Step form - 3 (Preview) | User preview | All the details will be previewd Edit functionality will take the user to the step | Should first-time users be guided with onboarding tooltips or tutorials? Is there a welcome deck or sample demo for new users? | NO
Subscription | Plans Selection | Feature listing | List down all the features offered | Any features that are available on both tiers? Any restrictions on the trial? Based on the plan - what would be the number of user | Only 1 pricing option, 7 day free trial. The trial will have no resteictions but will need a credit card for signing up which we will charge after 7 days.
| Confirmation | Payment details | Stripe integration Payment confirmation | Please confirm if you want to give a month trial and then the subscription will start | 7 Day trial
Dashboard | Navigation bar | Scatterplot x Company logo Menu items | Company details | Only one company is confirged post signup
| Featured section | Featured formats of PPT | Categories, Topics, Sub-categories
| PPT view | List of PPTs created | List and grid view
Slides Library | Search Slides
Filtering the Slides
Interactions with Slides : Key Talking Points, Add to Deck, Download
|  |  | - | -